## Team
Initials | First | Last | Email | GitHub Username
rx | Ruohuan | Xu | rxu28@stevens.edu | Rungerlas
Sb | Samarpan | Biswas | sbiswas@stevens.edu | SamarpanBiswas
Na | Nicholas | Apostolico | napostol@stevens.edu | NickApostolico
Kt | Kechao | Tu | ktu1@stevens.edu | KbyteTutu
Cs | Christian | Smith | csmith14@stevens.edu | Dioden
|  |  | GitHub Repository: | 2019fall-Group5-555B-Project
|  |  | Url： | https://github.com/KbyteTutu/2019fall-Group5-555B-Project

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Number of individuals is below 3000 | Na | Done
1 | US02 | Number of Families is below 1000 | Kt | Done
1 | US03 | No repeating Individuals in the Individuals list | Na | Done
1 | US04 | No repeating Families in the Families list | Kt | Done
1 | US05 | Display unique identifiers for each individuals | Rx | Done
1 | US06 | Display each individual (US05) in order by their unique identifiers | Rx | Done
1 | US07 | Display names of husbands and their unique identifiers | Sb | Done
1 | US08 | Display names of wives and their unique identifiers | Cs | Done
1 | US09 | Display names of husbands (US06), followed by unique family identifiers | Sb | Done
1 | US10 | Display names of wives (US07), followed by unique family identifiers | Cs | Done
2 | US11 | Fix the bugs - Same ID for a individual | Cs | Done
2 | US12 | Put all code into a class obey the OOP standard | Rx | Done
2 | US13 | Refact the individual | Kt | Done
2 | US14 | Refact the family builder | Kt | Done
2 | US15 | Check if individual information is valid(Age<150,input of Sex is Male/Female,etc) | Sb | Done
2 | US16 | Write the output to file Function. The output should be several TXT files. | Rx | Done
2 | US17 | Fix the bugs - Same ID for a individual | Cs | Done
2 | US18 | Check if family information is valid(Hus is man,wife is woman,etc) | Sb | Done
2 | US19 | Combine TestUnits provided by others | Na | Done
2 | US20 | Check those TestUnits and fix the bugs with the owner | Na | Done
3 | US21 | Calculate the average age of the children in each family | Na | Coding
3 | US22 | Calculate the average age of the man in each family | Na | Coding
3 | US23 | Calculate the average age of the woman in each family | Sb | Coding
3 | US24 | Calculate the average number of children per family | Sb | Coding
3 | US25 | Check for errors where death date occurs before birth date | Cs | Coding
3 | US26 | Check for errors where a dead person is married | Cs | Coding

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2019-09-25 | 40 |  | 0
2019-10-08 | 30 | 10 | 246 | 120 | 123

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Number of individuals is below 3000 | Na | Coding | 9 | 60 | 15 | 60 | Done
US02 | Number of Families is below 1000 | Kt | Coding | 9 | 60 | 15 | 60 | Done
US03 | No repeating Individuals in the Individuals list | Na | Coding | 9 | 60 | 30 | 60 | Done
US04 | No repeating Families in the Families list | Kt | Coding | 9 | 60 | 30 | 60 | Done
US05 | Display unique identifiers for each individuals | Rx | Coding | 9 | 60 | 30 | 60 | Done
US06 | Display each individual (US05) in order by their unique identifiers | Rx | Coding | 9 | 60 | 30 | 60 | Done
US07 | Display names of husbands and their unique identifiers | Sb | Coding | 9 | 60 | 25 | 60 | Done
US08 | Display names of wives and their unique identifiers | Cs | Coding | 9 | 60 | 25 | 60 | Done
US09 | Display names of husbands (US06), followed by unique family identifiers | Sb | Coding | 9 | 60 | 15 | 60 | Done
US10 | Display names of wives (US07), followed by unique family identifiers | Cs | Coding | 9 | 60 | 15 | 60 | Done
Review Results
Good
Keep doing:
Watch sports after meeting
Avoid:
Be late for meeting

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US11 | Fix the bugs - Same ID for a individual | Cs | Coding | 50 | 90
US12 | Put all code into a class obey the OOP standard | Rx | Coding | 50 | 90
US13 | Refact the individual | Kt | Coding | 50 | 90
US14 | Refact the family builder | Kt | Coding | 50 | 90
US15 | Check if individual information is valid(Age<150,input of Sex is Male/Female,etc) | Sb | Coding | 50 | 90 | 20 | 40 | Done
US16 | Write the output to file Function. The output should be several TXT files. | Rx | Coding | 50 | 90
US17 | Fix the bugs - Same ID for a individual | Cs | Coding | 50 | 90
US18 | Check if family information is valid(Hus is man,wife is woman,etc) | Sb | Coding | 50 | 90 | 20 | 40 | Done
US19 | Combine TestUnits provided by others | Na | Coding | 50 | 90 | 30 | 80 | Done
US20 | Check those TestUnits and fix the bugs with the owner | Na | Coding | 50 | 90 | 10 | 30 | Done

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US21 | Calculate the average age of the children in each family | Na | Coding | 40 | 75
US22 | Calculate the average age of the man in each family | Na | Coding | 40 | 75
US23 | Average Woman age | Sb | Coding | 40 | 75
US24 | Average number of children per family | Sb | Coding | 40 | 75
US25 | Death date before birth date | Cs | Coding | 40 | 75
US26 | Marriage of dead person | CS | Coding | 40 | 75
US27
US28
US29
US30

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description
US01 | Number of individuals is below 3000 | figure out whether the number of individuals is below 3000
US02 | Number of Families is below 1000 | figure out whether the number of families is below 1000
US03 | No repeating Individuals in the Individuals list | figure out whether there are repeating individuals and show the whole individual without repeating
US04 | No repeating Families in the Families list | figure out whether there are repeating families and show the whole families without repeating
US05 | Display unique identifiers for each individuals | Find all unique identifiers of each individuals and show all of them
US06 | Display each individual (US05) in order by their unique identifiers | Find all unique identifiers of each individuals and show all of them in the order of their identifiers
US07 | Display names of husbands and their unique identifiers | Find all the names of the husbands and their unique identifiers and display all of them
US08 | Display names of wives and their unique identifiers | Find all the names of the wives and their unique identifiers and display all of them
US09 | Display names of husbands (US06), followed by unique family identifiers | Find all names of husbands and order them by unique family identifier, then display all of them
US10 | Display names of wives (US07), followed by unique family identifiers | Find all names of wives and order them by unique family identifier, then display all of them
US11 | Fix the bugs - Same ID for a individual | Fix the bugs - Same ID for a individual
US12 | Put all code into a class obey the OOP standard | Put all code into a class obey the OOP standard
US13 | Refact the individual | Refact the individual
US14 | Refact the family builder | Refact the family builder
US15 | Check if individual information is valid(Age<150,input of Sex is Male/Female,etc) | Check if individual information is valid(Age<150,input of Sex is Male/Female,etc)
US16 | Write the output to file Function. The output should be several TXT files. | Write the output to file Function. The output should be several TXT files.
US17 | Fix the bugs - Same ID for a individual | Fix the bugs - Same ID for a individual
US18 | Check if family information is valid(Hus is man,wife is woman,etc) | Check if family information is valid(Hus is man,wife is woman,etc)
US19 | Combine TestUnits provided by others | Combine TestUnits provided by others
US20 | Check those TestUnits and fix the bugs with the owner | Check those TestUnits and fix the bugs with the owner
US21 | Average Children Age | Calculate the average age of the children in each family
US22 | Average Man Age | Calculate the average age of the man in each family
US23 | Average Woman age | Calculate the average age of the woman in each family
US24 | Average number of children per family | Calculate the average number of children per family
US25 | Death date before birth date | Check for errors where death date occurs before birth date
US26 | Marriage of dead person | Check for errors where a dead person is married